## drug interaction data
Drug Interaction Database - Milestone Task Tracking
Project Charter Approval
Project Charter | Milestone Name | Responsibility | Start Date | End Date | Complete
| Choose Project Topic | Louise Fear | 2024-01-22 | 2024-01-30 | Yes
| Choose Project Topic | James Laurence | 2024-01-22 | 2024-01-30 | Yes
| Choose Project Topic | Chris Whalen | 2024-01-22 | 2024-01-30 | Yes
| Choose Project Topic | Gabriela Mkonde | 2024-01-22 | 2024-01-30 | Yes
| Find Data Source | Louise Fear | 2024-01-22 | 2024-01-30 | Yes
| Project Charter Document | Louise Fear | 2024-01-22 | 2024-01-30 | Yes
| Project Charter Document | James Laurence | 2024-01-22 | 2024-01-30 | Yes
| Project Charter Document | Chris Whalen | 2024-01-22 | 2024-01-30 | Yes
| Project Charter Document | Gabriela Mkonde | 2024-01-22 | 2024-01-30 | Yes
| Project Schedule | Louise Fear | 2024-01-22 | 2024-01-30 | Yes
| Project Schedule | James Laurence | 2024-01-22 | 2024-01-30 | Yes
| Project Schedule | Chris Whalen | 2024-01-22 | 2024-01-30 | Yes
| Project Schedule | Gabriela Mkonde | 2024-01-22 | 2024-01-30 | Yes
| Project Charter Presentation | Louise Fear | 2024-01-22 | 2024-01-30 | Yes
| Project Charter Presentation | James Laurence | 2024-01-22 | 2024-01-30 | Yes
| Project Charter Presentation | Chris Whalen | 2024-01-22 | 2024-01-30 | Yes
| Project Charter Presentation | Gabriela Mkonde | 2024-01-22 | 2024-01-30 | Yes
Back-End Development
Data Acquisition/ETL | Milestone Name | Responsibility | Start Date | End Date | Complete
| Pick Important Attributes from XML File | James Laurence | 2024-01-30 | 2024-02-15 | Yes
| Pick Important Attributes from XML File | Chris Whalen | 2024-01-30 | 2024-02-15 | Yes
| Pick Important Attributes from XML File | Louise Fear | 2024-01-30 | 2024-02-15 | Yes
| Pick Important Attributes from XML File | Gabriela Mkonde | 2024-01-30 | 2024-02-15 | Yes
| Approve Important Attributes | James Laurence | 2024-01-30 | 2024-02-15 | Yes
| Approve Important Attributes | Chris Whalen | 2024-01-30 | 2024-02-15 | Yes
| Approve Important Attributes | Louise Fear | 2024-01-30 | 2024-02-15 | Yes
| Approve Important Attributes | Gabriela Mkonde | 2024-01-30 | 2024-02-15 | Yes
| Extract Important Attributes Using Georges Powershell Script | Louise Fear | 2024-01-30 | 2024-02-29 | Yes
| Extract Important Attributes Using Georges Powershell Script | James Laurence | 2024-01-30 | 2024-02-29 | Yes
| Extract Important Attributes Using Georges Powershell Script | Chris Whalen | 2024-01-30 | 2024-02-29 | Yes
| Convert XML into CSV | Louise Fear | 2024-01-30 | 2024-03-09 | Yes
| Convert XML into CSV | James Laurence | 2024-01-30 | 2024-03-09 | Yes
| CSV Data Cleaning | Louise Fear | 2024-01-30 | 2024-03-27 | Yes
| Import Data into SQL database | James Laurence | 2024-01-30 | 2024-03-27 | Yes
ERD | Milestone Name | Responsibility | Start Date | End Date | Complete
| Draw a rough sketch of the ERD | Chris Whalen | 2024-02-15 | 2024-03-09 | Yes
| Create Initial Version of ERD | Chris Whalen | 2024-02-15 | 2024-03-09 | Yes
| Review the ERD with the team | Chris Whalen | 2024-02-15 | 2024-03-09 | Yes
| Make necessary changes based on feedback | Chris Whalen | 2024-03-09 | 2024-03-20 | Yes
| Review updated version of ERD with the team | Chris Whalen | 2024-03-09 | 2024-03-20 | Yes
| Make necessary changes based on feedback | Chris Whalen | 2024-03-09 | 2024-03-20 | Yes
| Finalize the ERD | Chris Whalen | 2024-03-09 | 2024-03-20 | Yes
Data Dictionary | Milestone Name | Responsibility | Start Date | End Date | Complete
| List of Data Dictionary Elements | Gabriela Mkonde | 2024-02-29 | 2024-03-19 | Yes
| Review Data Dictionary with Team | Gabriela Mkonde | 2024-02-29 | 2024-03-19 | Yes
| Make Changes based on feedback | Gabriela Mkonde | 2024-03-19 | 2024-03-27 | Yes
| Finalize Data Dictionary | Gabriela Mkonde | 2024-03-19 | 2024-03-27 | Yes
DFD | Milestone Name | Responsibility | Start Date | End Date | Complete
| Use the ERD and Data Dictionary to create a DFD | Gabriela Mkonde | 2024-02-15 | 2024-03-09 | Yes
| Review the DFD with the team | Gabriela Mkonde | 2024-03-09 | 2024-03-19 | Yes
| Make necessary changes based on feedback | Gabriela Mkonde | 2024-03-19 | 2024-03-27 | Yes
| Review the updated DFD with the team | Gabriela Mkonde | 2024-03-19 | 2024-03-27 | Yes
| Finalize DFD | Gabriela Mkonde | 2024-03-19 | 2024-03-27 | Yes
Database Schema Creation | Milestone Name | Responsibility | Start Date | End Date | Complete
| DDL Script to create all tables and relationships | James Laurence | 2024-03-09 | 2024-03-20 | Yes
| Import Data into SQL database (TEST) | Louise Fear | 2024-03-19 | 2024-03-27 | Yes
| Import Data into SQL database (TEST) | James Laurence | 2024-03-19 | 2024-03-27 | Yes
| Update DDL script as required and retest | James Laurence | 2024-03-09 | 2024-03-27 | Yes
| Finalize SQL Script | James Laurence | 2024-03-09 | 2024-03-27 | Yes
| Import Cleaned Data into SQL database | Louise Fear | 2024-03-19 | 2024-03-27 | Yes
SQL Query Testing | Milestone Name | Responsibility | Start Date | End Date | Complete
| SQL Database Query Testing | Louise Fear | 2024-03-27 | 2024-04-05 | Yes
| SQL Query Validation | Louise Fear | 2024-03-27 | 2024-04-05 | Yes
| SQL Query Functional Testing - ACID Properties | Louise Fear | 2024-03-27 | 2024-04-05 | Yes
| Finalize SQL Query Testing | Louise Fear | 2024-03-27 | 2024-04-05 | Yes
Front-End Development
UI Development | Milestone Name | Responsibility | Start Date | End Date | Complete
| Research best practices for drug information UI | Chris Whalen | 2024-03-27 | 2024-04-05 | Yes
| Sketch initial design ideas | Gabriela Mkonde | 2024-03-27 | 2024-04-05 | Yes
| Refine sketches based on feedback | Gabriela Mkonde | 2024-03-27 | 2024-04-05 | Yes
| Create a detailed UI design | Gabriela Mkonde | 2024-03-27 | 2024-04-05 | Yes
| Review and finalize the design | Gabriela Mkonde | 2024-03-27 | 2024-04-05 | Yes
| Set up the development environment | James Laurence | 2024-03-27 | 2024-04-05 | Yes
| Set up the development environment | Louise Fear | 2024-03-27 | 2024-04-05 | Yes
| Set up the development environment | Gabriela Mkonde | 2024-03-27 | 2024-04-05 | Yes
| Set up the development environment | Chris Whalen | 2024-03-27 | 2024-04-05 | Yes
| Break down the UI design into components | Gabriela Mkonde | 2024-03-27 | 2024-04-05 | Yes
| Develop a UI test plan | Gabriela Mkonde | 2024-03-27 |  | No
| Execute the test cases |  | 2024-03-27 |  | No
Project Charter and Presentation - Final
Project Charter | Milestone Name | Responsibility | Start Date | End Date | Complete
| Revise Project Charter Documentation | James Laurence | 2024-03-28 | 2024-04-12 | No
| Revise Project Gantt Chart | James Laurence | 2024-03-28 | 2024-04-12 | No
| Project Final Documentation | James Laurence | 2024-03-28 | 2024-04-12 | No
| Project Final Documentation | Louise Fear | 2024-03-28 | 2024-04-12 | No
| Project Final Documentation | Gabriela Mkonde | 2024-03-28 | 2024-04-12 | No
| Project Final Documentation | Chris Whalen | 2024-03-28 | 2024-04-12 | No
| Project Final Presentation | James Laurence | 2024-03-28 | 2024-04-12 | No
| Project Final Presentation | Louise Fear | 2024-03-28 | 2024-04-12 | No
| Project Final Presentation | Gabriela Mkonde | 2024-03-28 | 2024-04-12 | No
| Project Final Presentation | Chris Whalen | 2024-03-28 | 2024-04-12 | No
Scrums/Meetings
| Milestone Name | Responsibility | Start Date | End Date | Complete
| Scrum 1 | Team | 2024-02-02 | 2024-02-09 | Yes
| Scrum 2 | Team | 2024-02-09 | 2024-02-16 | Yes
| Scrum 3 | Team | 2024-02-16 | 2024-02-23 | Yes
| February Monthly Meeting | Team | 2024-02-02 | 2024-02-29 | Yes
| Scrum 4 | Team | 2024-02-23 | 2024-03-01 | Yes
| Scrum 5 | Team | 2024-03-01 | 2024-03-08 | Yes
| Scrum 6 | Team | 2024-03-08 | 2024-03-22 | Yes
| March Monthly Meeting | Team | 2024-03-01 | 2024-04-02 | Yes
| Scrum 7 | Team | 2024-03-22 | 2024-04-05 | No
------------------------------------------------------------------ Activities Out Of Scope ---------------------------------------------------------------------------------
Predictive Modelling
Develop the predictive algorithm | Milestone Name | Responsibility | Start Date | End Date | Complete
| Define the algorithm requirements based on the project’s data |  |  |  | No
| Write the algorithm code |  |  |  | No
Test the algorithm | Milestone Name | Responsibility | Start Date | End Date | Complete
| Identify a representative subset of data for testing |  |  |  | No
| Run the algorithm and check the results for accuracy |  |  |  | No
Refine the algorithm based on test results | Milestone Name | Responsibility | Start Date | End Date | Complete
| Identify any issues or inefficiencies in the algorithm |  |  |  | No
| Refine the algorithm code to address these issues |  |  |  | No
Deploy the algorithm | Milestone Name | Responsibility | Start Date | End Date | Complete
| Prepare the deployment environment |  |  |  | No
| Check the accessibility of the algorithm for practical use |  |  |  | No
Verify the algorithm accessiblity | Milestone Name | Responsibility | Start Date | End Date | Complete
| Test the deployed algorithm for functionality. |  |  |  | No
| Check the accessibility of the algorithm for practical use |  |  |  | No
Check model accuracy | Milestone Name | Responsibility | Start Date | End Date | Complete
| Mean Absolute Error (MAE) |  |  |  | No
| Root Mean Squared Error (RMSE) |  |  |  | No

## time-tracking
Time Tracking
ERD
Started By | Ended By | Start Date | End Date | Start Time | End Time | Duration
Chris Whalen | Chris Whalen | 2024-03-06 | 2024-03-06 | 12:13:20 PM | 12:35:37 PM | 00:22:17
Chris Whalen | Chris Whalen | 2024-03-04 | 2024-03-04 | 12:07:12 PM | 01:25:52 PM | 01:18:40
Chris Whalen | Chris Whalen | 2024-02-28 | 2024-02-28 | 12:15:55 PM | 01:14:40 PM | 00:58:45
Chris Whalen | Chris Whalen | 2024-02-27 | 2024-02-27 | 04:03:29 PM | 04:35:14 PM | 00:31:45
Chris Whalen | Chris Whalen | 2024-02-27 | 2024-02-27 | 03:38:37 PM | 04:00:39 PM | 00:22:02
Total | [5 empty] | 03:33:29